## document_data
title | document_text
Phụ lục sửa đối bổ sung hợp đồng, Thư trình số HGU-MLT-00113-17 nhận ngày 28/06/2017 | “BẠN Ql DUONG SAT COT Ls cane VAN AN DEN CONG TY SYSTRA SA ` THẤU DVIV TH DA ‘a\ Số đấn:......4-CH2......... ‘¦ an] TUYỂN ĐƯỜNG SAT 4 ĐTTĐTPHN DOAN Nga a a at er aes Kính gửi: Ông Kim Do Gyoon - Giám đốc Dự án mm 7 Liên Danh Hyundai E&C - Ghella Địa chỉ: Tang 18, Tòa nhà VIT — 519 Kim Mã, Ngọc Khánh, Hà Nội ĐT: 84-24 32 37 3461 Fax: 84-24-32 37 34 62 Ngày: 10/08/2017 CV số: PIC-MLT-02340-17-V G Đồng kính Ông Nguyễn Cao Minh ~ Trưởng Ban gửi: Ban Quản lý Đường sắt đô thị Hà Nội (MRB) Địa chỉ: Tòa nhà CC-2 khu đô thị mới Đồng Tàu, Hoàng Mai, Hà Nội ĐT: 84-4-39 43 5127 Fax: 84-4-39 43 51 26 Về việc: CP03 — Phụ lục sửa đối bổ sung hợp đồng Thư trình số HGU-MLT-00113-17 nhận ngày 28/06/2017 Thưa Ông, Sau khi rà soát dự thảo Phụ lục sửa đổi bd sung hợp đồng nhận được như đề cập ở trên, PIC có nhận xét sau => Dự thảo bị từ chối. Đề nghị xem những nhận xét dưới đây và phụ lục để biết thêm chỉ tiết. Nhận xét chung: ¢ Dự thảo nhận được đề cập về một số tài liệu đính kèm mà vẫn chưa được in và trình cùng với đề xuất. Liên quan đến số tiền 40 triệu USE yêu cầu thanh toán trong tài liệu hiện rà soát, lẽ ra tối thiểu HGU cần lập một bộ tài liệu hoàn chỉnh và rõ ràng. © Nói chung, PIC không đồng ý với nguyên tắc của tài liệu đã phát hành. Thực vậy, sau khi rà soát tài liệu này, xem xét rằng kể từ khi công bố chính thức Dữ liệu Khởi công, yêu cầu đang trình bày đến nay không thể hiện bất kỳ nội dung chỉ tiết nào. Yêu cầu này cần được thực hiện theo hợp đồng và lập một báo cáo yêu cầu thay đổi, bao gồm: toàn bộ tài liệu như thường lệ, giải trình và chi tiết cụ thể đối với kiểu yêu cầu gia han thời gian này, dự toán phân tích chỉ phí cụ thể liên quan. Sau khi phê duyệt thì Báo cáo Thay đổi này sẽ được đưa vào Phụ lục sửa đổi hợp đồng để ký kết e_ Chí phí: Không cung cấp bất ky chi tiết nào, sao HGU có thể nghĩ là sẽ nhận được cau trả lời tích cực cho yêu cầu này? Chủ đầu tư và/hoặc Kỹ su’ sẽ rà soát và đánh giá yêu cầu nhận được trên cơ sở nào? HGU đã chuẩn bị việc này hơn 6 tháng mà đến nay, hồ sơ nhận được từ HGU vẫn rất đáng ngạc nhiên. Tinh trang này không thể chấp nhận được. Để thông tin, giá trị yêu cau như sau: L.. mà : - [Noite ¦ _ _Ngoại tệ,... -¦ ¬' ¦ Dos wD, ¦ = ¦ mm ..¦ THÔNG TIN 12/05/2014 ¦ 2913757 ¦ 2112000 Ị _„ L: TỐNG GIÁ TRỊ YÊU CAUTHEODONGTIEN ¦ — 304233935289 8210972 13 459 766 m QUYĐỔISANGVND TT” 304233935289, 239247771418. 284270257920. 627751964627 ¦ Fe QUY ĐỐI SANG USD __— _ 14405016 ! 11328019 ¦ 13.459 766 ¦ 39 192 801 Do đó, để có thể xem xét thêm, yêu cầu HGU lập yêu cầu của mình một cách thích hợp và hoàn chỉnh để Chủ đầu tư/Kỹ sư xem xét thêm. —O- Van phòng Dự án Metro Ha Nội SYSTRA Tang 12 : loa Tháp VP Hèa Binh, số 106 Hoang Quốc Việt * Quan Cầu Giấy ¢ Hà Nội * Việt Nam ĐT; +84 4 3791 85 40 © Fax: +84 A 37 91 85 44 e Website: www.systra.com
CP01 — Proposal for payment of the withholding amount related to the provisional calculation for Price Adjustment in IPC 56 | DAELIM INDUSTRIAL Co., LTD. DAELIM We vn, Me ieee KỆ Ai, Dmy Tan See, Cal Song wa dụ Cat Ger Are và Hà toi, Veetnain Th St lt V226 0155 For, Ce pt tel VITC WVNgbi tố, VWOWV.CEBLTI.Gt.Km Date : March 02 2023 Ref. No.: DLM-MLT-00001-23-E To: Mr. Nguyen Cao Mind — General Director Hanoi Metropolitan Railway Management Board (MRB) Address: Building CC-2. Dong Tau Urban Area, Hoang Mai Dist.. Hanoi Tel: 84-24-39 43 51 27 Fax: 84-24-39 43 51 26 To: Mr. Alain BECHEREALU - Project Director Systra Hanoi Metro Project Office Address: 12 floor, HOA BINH International Towers, 106 Hoang Quot Viet, Can Gray Dist., Hanoi City, Vice Nam Tel: 84-24-37 91 85 40 Fax: 84-24-37 91 85 44 Subject: Co01 — Proposal for payment of the withholding amount related to the provisional calculation for Price Adjustment in IPC 56 Dear Sits, In IPC 56, according to PIC's provisional calculation by comparing two different indices, the provisional price adjustment has resulted in a rather unrealistic amount. MRB/PIC is holding an equivalent amount of approximately Up$3.4 million in the Contractor's completed value, accordingly. This has greatly affected the Contractor's financial cash flow over a long period of time. After reviewing some of the Vietnamese economic statistics since 2012 as shown in the table below, it is obvious that the cost of all components in economic activities have increased during that period. Ns. “alex/Year Unit] 2012 2013 2014 2015 — 2016 208 1 2019 2020 2021 1 Mimmwmwages JUSD¦ 20000 ¦ 23500 ¦ 27000 ¦ 31000 35000 ¦ 37500 ¦ 39860 ; 41800 44200 ¦ 44200 2 CPIQ010 100) 1% 129% 1380 ¦ 1436 ¡ His : 148.4 1536. 159.1 ° 163% 1688 19 3 GDP deflator % đói ¦ 1458 474 l$34 1587 ¦ 161.5 1636 1672 ¦ 4 — ToÏupon (year % a ¦ 6ó ¦ 41! o6 ¦ 22 zs ¦ 3£ 28 32. is ¦ (Resource data: https: “tradingeconomics.com; hips. data worldbank.org, Iiips. www. geo.got vs) Based on the above economic data, the Contractor realizes that the data on the Consumer Price Index (CPI), GDP Deflation and Inflation is the most accurate reflection of the general fluctuations of the market prices (materials, labor and equipment). Therefore, these indicators have been selected to apply for the calculation of the Price Adjustment value according to the quantities and completion time of the Works of Co01 and the calculation formulas in accordance with the relevant Contract Conditions. Thereby, the calculation results of Co01's price index will give a positive value that accurately reflects the growth rate of economic statistics as following table: . ITEM : VfD USD Equi. USD Total Amount of Price Adjustment - i ! VIETNAM ECONOMICS DATA - CPI _ 149.888.737.158 3.345.644 954] 106 - (CASE 1) : ị ———————— Total Amount of Price Adjustment - : Ị VIETNAM ECONOMICS DATA - GDP DEFLATOR 109.373.271.743 1.703.843 6.947.049 ] (CASE 2) : j Total Amount of Price Adjustment - ' VIFTNAM ECONOMICS DATA - INFLATION 97.205.999 805 1.575.360 6.235.283 (CASE 3) 12
Contract Package No 06: Appointment of DB members (Reply to VIAC letter 1679/VIAC) | WU) \ Í ng SONU JOINT VENTURE ALSTOM == THALES Hanol, 11/01/2022 To the attention of: Vietnam International Arbitration Centre 6th Floor, VCCI Tower, No.9 Dao Duy Anh St., Dong Da Dist., Hanoi, Vietnam Copy to: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son - Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Subject: Contract Package No 06: Appointment of DB members (Reply to VIAC letter 1679/VIAC) UJV Letter Reference No: UJV-MLT-00015-22-E-UJV Reference to Letter No / Date: a. 1679/VIAC, dated 29/12/2021 b. 2337/DSDT-DA1, received 21/12/2021 c. UJV-MLT-00822-21-E-UJSV,dated 13/09/2021 Dear Vu Thi Hang, We acknowledge receipt of VIAC letter ref. [a], whereby VIAC notified some matters to MRB and UJV. Please see hereafter UJV's response: 4. Regarding MRB letter ref [b], in which, MRB informed VIAC that MRB and UJV are in the middle of “finding solutions to deal with arising issues, and to share the difficulties with MRB in complying with required steps to establish DB pursuant to Vietnamese laws”, UJV would like to remind that pursuant to the Heads of Terms signed on 7 August 2020 between UJV and MRB, a Contract Amendment mainly focusing on Extension of Time and financial compensation should have been finalized and agreed by 31 December 2020. Despite considerable efforts made by UJV and more than 1 year from the planned date, the Contract Amendment has not been signed yet due to many unresolved issues that prevent the Parties from finding the necessary final agreement. In these circumstances, UJV has sent its notification of Dispute Board Appointment with the CV of Mr. Vincent Leloup through above captioned letter [c]. MRB has then failed to approve UJV's nominated DB member by requiring to receive many unreasonable further information (ie: Request to provide proof of affiliation to a Security Social system of a DB member). Considering the very low progress on the Contract Amendment negotiation, UJV was left with no other choices but to go for Dispute Board’s Decision. 2. In relation with the payment of appointment fees please rest assured that UJV is in the process of paying the corresponding fees and could also make another payment, on behalf of MRB. UJV-MLT-00015-22-E-UJV dated: 11/01/2022 pooe t2 ¦ ALSTOM Transport S.A. - HANO! LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel, + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
Contract Package No 06: Payment of Appointment of DB members | Wh ÍjDNirarue JOINT VENTURE ALSTOM oom THALES Hanoi, 13/01/2022 To the attention of: Vietnam International Arbitration Centre 6th Floor, VCCI Tower, No.9 Dao Duy Anh St., Dong Da Dist, Hanoi, Vietnam Copy to: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Rafway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Raiway Management Board (MRB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hoang Mai, Hanoi Subject: Contract Package No 06: Payment of Appointment of DB members UJV Letter Reference No: UJV-MLT-00025-22-E-UJV Reference to Letter No / Date: a. UJV-MLT-00015-22-E-UJV, dated 11/01/2022 Dear Vu Thi Hang, Further to our letter ref [a], whereby we informed you that your request for paying Appointment service charges has been being processed and we could also make another payment on behalf of the Employer (knowing that the Employer is in the difficulty of paying this fee). We hereby notify you that UJV has paid in full the Appointment service charges for both Parties. Therefore, VIAC shall make all reasonable effort to appoint DB members. We are looking forward to hearing from you. pete Project Director Unincorporated Joint Venture On behalf of Unincorporated Joint Venture ¦ UJV-MLT-00026-22-E-UJV dated: 13/01/2022 Pege 1/2 ALSTOM Transport S.A. - HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 — Fax: +84 (0)24 3967 4999
Contract Package No 06: Impact of Covid-19 - Submission of In#11 ¦ | LẦN UNINCORPORATED . INT VENTURE ASTM == THALES Hand, 25/01/2021 To the attention of: Mr. Philippe BLANCHO - SYSTRA Project Director System Hand Metro Project Office 12" floor — Hoa Bin Building, 106 Hong Quot Viet Street, Can Gray District, Hand Copy to: Mr. Nguyen Cao Min - General Director Hand Metropolitan Railway Management Board (MB) CC2 Building, Dong Tau Urban Area, Think List, Hong Mai, Hand Mr. Nguyen Ba Son - Manager of Project Implementation (PID1 Management) Hand Metropolitan Railway Management Board (MB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hong Mai, Hand Subject: Contract Package No 06: Impact of Covid-19 - Submission of In#11 ¦ UV Letter Reference No: UV-LT-00060-21-E-UV Reference to Letter No/ Date: a. IC-LT-07467-20-E received 24/12/2020 b. UV-LT-01230-20-E dated 17/12/2020 c. IC-LT-07049-20-E received 04/12/2020 d. UV-LT-01133-20-E dated 25/11/2020 : e. PG-LT-06516-20-E received 05/11/2020 f. UV-LT-01089-20-E dated 28/10/2020 g. IC-LT-05760-20-E received 02/20/2020 h. UV-LT-00981-20-E dated 28/09/2020 1. IC-LT-05070-20-E received 26/08/2020 J. UV-LT-00867-20-E dated 21/08/2020 “ k. IC-LT-04578-20-E received 03/08/2020 c 1. UV-LT-00781-20-E dated 21/07/2020 5 F m. IC-LT-03854-20-E received 06/07/2020 a\ 4, n. UV-LT-00669-20-E dated 18/06/2020 % Nj o. IC-LT-03030-20-E received 26/05/2020 § p. UV-LT-00538-20-E dated 18/05/2020 q. IC-LT-01610-20-E received 14/04/2020 Dear Sir, Please find attached the Interim Claim #11 linked to the impact of Covid-19, with cut-off date 25 December 2020. ¦ As the event is continuing we will continue to provide updates of the Claim on a monthly basis in accordance with Clause ' 20.1 of the Conditions of Contract. Please rest assured that UV is doing its best efforts to mitigate the continuing impacts of the Covid-19 on the Project. UV-LT-00060-21-E-UV dated: 25/01/2021” page tr ¦ ASTM Transport S.A. - ANI LINE 3 / C08 Project Office ¦ Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cup Nam Ward, Loan Kim District, Hand, Vietnam ¦ Tel: + 84 (0)24 3956 4999 — Fax: +84 (0)24 3967 4999 ¦ Ww 1
Contract Package No 06: Impact of Covid-19 - Submission of In#11 ¦ | i nN CLE ALSTON —— THALES Hanoi, 15/02/2022 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. David CHEVALLIER - SYSTRA Acting Project Director Systra Hanoi Metro Project Office 412% floor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Request to improve the submission of as-built drawing „ UJV Letter Reference No: UJV-MLT-00084-22-E-UJV Reference to Letter No/ Date: [a] PIC-MLT-04719-21-B, received 05/10/2021 Dear Sirs, UJV acknowledges receipt PIC letter reference [a], whereby PIC has raised the concern about the submission of as- built drawing progress which has been too slow compared to the package’s progress. PIC has requested UJV to submit as-built drawing progressively, corresponding to the progress of the work package. UJV would like to respond as follows: UJV's quality team has worked closely with its counterpart on PIC’s side. Some resolutions has been achieved. Therefore, please find in the attachment the completed list of drawing which will be submitted as As-built drawing with the target submission date. UJV would like to get PIC's agreement on the exhaustibility of the list then we could focus on the submission of the drawing. The submission progress is resumed by the table below which is monitored and shared during weekly meeting with PIC. It is noted that for RSK, the as-built drawings are currently under discussion with between PIC's Quality and PIC’s Engineering teams, UJV is waiting for PIC comments on this topic. The target submission date for drawings related to depot and underground works is purely depended on the progress of Civil works Contractors. In additional, UJV would like to raise the point on the installation drawings which need only affix the as-built stamp (as it has no change or minor modification displayed through red-mark). For these drawings, it is difficult to collect the full set from MRB with their signature as MRB would only sign when the full package is completed. This would delay the as-built submission progress. To improve, UJV would like to print the scanned version these drawings and affix as-built stamp then submit to PIC. This categorization of drawing is defined in the last column of the list "Submission Type”. UJV-MLT-00084-22-E-UJV ngay: 15/02/2022 Page 172 ¦ ALSTOM Transport S.A. - HANOI LINE 3/ CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - - Fax: +84 (0)24 3967 4999 Ls 24 ALSror`
Contract Package No 06: Request to improve the submission of as-built drawing | i nN CLE ALSTON —— THALES Hanoi, 15/02/2022 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. David CHEVALLIER - SYSTRA Acting Project Director Systra Hanoi Metro Project Office 412% floor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Request to improve the submission of as-built drawing „ UJV Letter Reference No: UJV-MLT-00084-22-E-UJV Reference to Letter No/ Date: [a] PIC-MLT-04719-21-B, received 05/10/2021 Dear Sirs, UJV acknowledges receipt PIC letter reference [a], whereby PIC has raised the concern about the submission of as- built drawing progress which has been too slow compared to the package’s progress. PIC has requested UJV to submit as-built drawing progressively, corresponding to the progress of the work package. UJV would like to respond as follows: UJV's quality team has worked closely with its counterpart on PIC’s side. Some resolutions has been achieved. Therefore, please find in the attachment the completed list of drawing which will be submitted as As-built drawing with the target submission date. UJV would like to get PIC's agreement on the exhaustibility of the list then we could focus on the submission of the drawing. The submission progress is resumed by the table below which is monitored and shared during weekly meeting with PIC. It is noted that for RSK, the as-built drawings are currently under discussion with between PIC's Quality and PIC’s Engineering teams, UJV is waiting for PIC comments on this topic. The target submission date for drawings related to depot and underground works is purely depended on the progress of Civil works Contractors. In additional, UJV would like to raise the point on the installation drawings which need only affix the as-built stamp (as it has no change or minor modification displayed through red-mark). For these drawings, it is difficult to collect the full set from MRB with their signature as MRB would only sign when the full package is completed. This would delay the as-built submission progress. To improve, UJV would like to print the scanned version these drawings and affix as-built stamp then submit to PIC. This categorization of drawing is defined in the last column of the list "Submission Type”. UJV-MLT-00084-22-E-UJV ngay: 15/02/2022 Page 172 ¦ ALSTOM Transport S.A. - HANOI LINE 3/ CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - - Fax: +84 (0)24 3967 4999 Ls 24 ALSror`
Contract Package No 06: Updated list of SONO documents pending for approval | VD UNINCORPORATED JOINT VENTURE ALSTOM <j: THALES Hanoi, 14/02/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son - Vice General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU ~ SYSTRA Project Director Systra Hanoi Metro Project Office 42% floor — Hoa Binh Building,106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Updated list of SONO documents pending for approval UJV Letter Reference No: UJV-MLT-00085-23-E-UJV Reference to Letter No/ Date: a. Letter MRB 828/DSDT-DA1 received 18/05/2020 b. UJV-MLT-00731-22-B-UJV, dated 31/10/2022 c. UJV-MLT-00608-22-E-UJV, 12/09/2022 Dear Sirs, We refer to our letter ref [c] whereby due to delay in the Employer's approval process, we expressed our willingness to support you to speed up this process. In particular, in order to not waste any more time, we have collected 461 documents from MRB*s office, arranged those documents and invited MRB to come and complete the final steps (sign and stamp) at UJV's office. Indeed, we have proposed MRB staff to come to stamp for few hours a day and we are even ready to work overtime with you during the weekend to finish the process. However, through several emails exchanged, we understand that you are not able to cooperate with us in completing documentation works following our proposal. We, therefore, would like to return those collected documents to you. On top of that, following our letter ref [b], we would like to update the list of documents which have been granted SONO status by the Engineer but are still pending for approval from the Employer (excluding documents that no need approval according to letter ref [a]). As of 13 Feb 2023, there are 324 documents which were granted SONO status by the Engineer but have not been received approval from the Employer. Of these pending documents, it took, on an average, 200 days (6.5 months) for review and there are number of documents which have been granted SONO since May 2020. This delay, indeed, has been affecting the completion of CP06's works which is beyond our control. Thus, UJV, once again, would like to request the Employer to quickly approve for the SONO documents listed in the attachment 1. Your prompt action is highly appreciated. UJV-MLT-00085-23-E-UJV dated: 14/02/2023 ALSTOM Transport S.A. — HANOI LINE 3/ CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 — Fax: +84 (0)24 3967 4999 VD UNINCORPORATED JOINT VENTURE ALSTOM <j: THALES Hanoi, 14/02/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son - Vice General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU ~ SYSTRA Project Director Systra Hanoi Metro Project Office 42% floor — Hoa Binh Building,106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Updated list of SONO documents pending for approval UJV Letter Reference No: UJV-MLT-00085-23-E-UJV Reference to Letter No/ Date: a. Letter MRB 828/DSDT-DA1 received 18/05/2020 b. UJV-MLT-00731-22-B-UJV, dated 31/10/2022 c. UJV-MLT-00608-22-E-UJV, 12/09/2022 Dear Sirs, We refer to our letter ref [c] whereby due to delay in the Employer's approval process, we expressed our willingness to support you to speed up this process. In particular, in order to not waste any more time, we have collected 461 documents from MRB*s office, arranged those documents and invited MRB to come and complete the final steps (sign and stamp) at UJV's office. Indeed, we have proposed MRB staff to come to stamp for few hours a day and we are even ready to work overtime with you during the weekend to finish the process. However, through several emails exchanged, we understand that you are not able to cooperate with us in completing documentation works following our proposal. We, therefore, would like to return those collected documents to you. On top of that, following our letter ref [b], we would like to update the list of documents which have been granted SONO status by the Engineer but are still pending for approval from the Employer (excluding documents that no need approval according to letter ref [a]). As of 13 Feb 2023, there are 324 documents which were granted SONO status by the Engineer but have not been received approval from the Employer. Of these pending documents, it took, on an average, 200 days (6.5 months) for review and there are number of documents which have been granted SONO since May 2020. This delay, indeed, has been affecting the completion of CP06's works which is beyond our control. Thus, UJV, once again, would like to request the Employer to quickly approve for the SONO documents listed in the attachment 1. Your prompt action is highly appreciated. UJV-MLT-00085-23-E-UJV dated: 14/02/2023 ALSTOM Transport S.A. — HANOI LINE 3/ CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 — Fax: +84 (0)24 3967 4999 VD UNINCORPORATED JOINT VENTURE ALSTOM <j: THALES Hanoi, 14/02/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son - Vice General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU ~ SYSTRA Project Director Systra Hanoi Metro Project Office 42% floor — Hoa Binh Building,106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Updated list of SONO documents pending for approval UJV Letter Reference No: UJV-MLT-00085-23-E-UJV Reference to Letter No/ Date: a. Letter MRB 828/DSDT-DA1 received 18/05/2020 b. UJV-MLT-00731-22-B-UJV, dated 31/10/2022 c. UJV-MLT-00608-22-E-UJV, 12/09/2022 Dear Sirs, We refer to our letter ref [c] whereby due to delay in the Employer's approval process, we expressed our willingness to support you to speed up this process. In particular, in order to not waste any more time, we have collected 461 documents from MRB*s office, arranged those documents and invited MRB to come and complete the final steps (sign and stamp) at UJV's office. Indeed, we have proposed MRB staff to come to stamp for few hours a day and we are even ready to work overtime with you during the weekend to finish the process. However, through several emails exchanged, we understand that you are not able to cooperate with us in completing documentation works following our proposal. We, therefore, would like to return those collected documents to you. On top of that, following our letter ref [b], we would like to update the list of documents which have been granted SONO status by the Engineer but are still pending for approval from the Employer (excluding documents that no need approval according to letter ref [a]). As of 13 Feb 2023, there are 324 documents which were granted SONO status by the Engineer but have not been received approval from the Employer. Of these pending documents, it took, on an average, 200 days (6.5 months) for review and there are number of documents which have been granted SONO since May 2020. This delay, indeed, has been affecting the completion of CP06's works which is beyond our control. Thus, UJV, once again, would like to request the Employer to quickly approve for the SONO documents listed in the attachment 1. Your prompt action is highly appreciated. UJV-MLT-00085-23-E-UJV dated: 14/02/2023 ALSTOM Transport S.A. — HANOI LINE 3/ CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 — Fax: +84 (0)24 3967 4999 VD UNINCORPORATED JOINT VENTURE ALSTOM <j: THALES Hanoi, 14/02/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son - Vice General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU ~ SYSTRA Project Director Systra Hanoi Metro Project Office 42% floor — Hoa Binh Building,106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Updated list of SONO documents pending for approval UJV Letter Reference No: UJV-MLT-00085-23-E-UJV Reference to Letter No/ Date: a. Letter MRB 828/DSDT-DA1 received 18/05/2020 b. UJV-MLT-00731-22-B-UJV, dated 31/10/2022 c. UJV-MLT-00608-22-E-UJV, 12/09/2022 Dear Sirs, We refer to our letter ref [c] whereby due to delay in the Employer's approval process, we expressed our willingness to support you to speed up this process. In particular, in order to not waste any more time, we have collected 461 documents from MRB*s office, arranged those documents and invited MRB to come and complete the final steps (sign and stamp) at UJV's office. Indeed, we have proposed MRB staff to come to stamp for few hours a day and we are even ready to work overtime with you during the weekend to finish the process. However, through several emails exchanged, we understand that you are not able to cooperate with us in completing documentation works following our proposal. We, therefore, would like to return those collected documents to you. On top of that, following our letter ref [b], we would like to update the list of documents which have been granted SONO status by the Engineer but are still pending for approval from the Employer (excluding documents that no need approval according to letter ref [a]). As of 13 Feb 2023, there are 324 documents which were granted SONO status by the Engineer but have not been received approval from the Employer. Of these pending documents, it took, on an average, 200 days (6.5 months) for review and there are number of documents which have been granted SONO since May 2020. This delay, indeed, has been affecting the completion of CP06's works which is beyond our control. Thus, UJV, once again, would like to request the Employer to quickly approve for the SONO documents listed in the attachment 1. Your prompt action is highly appreciated. UJV-MLT-00085-23-E-UJV dated: 14/02/2023 ALSTOM Transport S.A. — HANOI LINE 3/ CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 — Fax: +84 (0)24 3967 4999
Contract Package No 06: Reply PIC’s comments on Installation Design Report: SIT-S4-MSS Interface Integration Test Report S01. | Wy) \ ae JOINT VENTURE ALSTOM ‘aa. THALES Hanoi, 21/02/2023 To the attention of: Mr. Alain BECHEREAU - SYSTRA Project Director Systra Hanoi Metro Project Office 121 floor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Copy to: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Subject: Contract Package No 06: Reply PIC’s comments on Installation Design Report: SIT-S4-MSS Interface Integration Test Report S01. UJV Letter Reference No: UJV-MLT-00097-23-E-UJV Reference to Letter No / Date: a. PIC-MLT-04416-22-B, received 26/12/2022 Dear Sirs, UJV acknowledges receipt of PIC's letter [a] in which PIC commented on Installation Design Report: SIT-S4-MSS Interface Integration Test Report S01: “The S!T-S4 - MSS Interface Integration Test not fully performed as SIT-S4 — MSS/CBTC Interface integration test procedure defined at item 1.2 Scope: This document is applicable to all MSS equipment of HNL3 Project in station S01 and Backup room. CP06 is requested to accelerate the demonstration of the remaining test activity - Appendix 1: SIT-S4 Test sheet at backup room (Steps from 1 to 87) at BOCC SER". UJV would like to respond as follows: According to SIT-S4 - MSS/CBTC Interface integration test procedure at item 1.2 Scope which defined: This document is applicable to all MSS equipment of HNL3 Project in station S01 and Backup room, UJV confirms SIT-S4 test are performed for both S01 station and Backup room but as separated activities. Consequently SIT-S4 reports will be submitted to PIC/MRB separately for S01 station (as document no. UJV-IMP-TRE-SIG-L00-40169-E-T200-2.10, SIT-S4 - MSS Interface Integration Tests Report - S01) and for Backup Room (as document no. UJV-IMP-TRE-SIG-L00-40548, SIT-S4 - MSS Interface Integration Tests Report - Backup Room) same as defined in next update of Submittal Schedule. UJV confirms the SIT-S4 test activity in Backup Room has no link or impact to test results and the submission of SIT-S4 report for S01 station. Note that, the implementation of the procedure and report SIT-S4 is similar to the implementation of other procedures and reports which was completed, such as SIT-S1 - SMIO / Trackside & Station Equipment Integration Test Procedure [ UJV-MLT-00097-23-E-UJV dated: 21/02/2023 Page 1/2 ALSTOM Transport S.A. — HANOI LINE 3/ CP06 Project Office nt Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999 ⁄4 ALSTo¿
Contract Package No 06: Approval of the outline of the load test inspection Sublset | ; L1 Jperoro JOINT VENTURE ALSTOM eR THALES - Hanoi, 21/02/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU - SYSTRA Project Director Systra Hanoi Metro Project Office 12% floor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi . Contract Package No 06: Approval of the outline of the load test inspection Sublset; (response to MRB letter 230/DSDT-KTTD) UJV Letter Reference No: UJV-MLT-00098-23-E-UJV Reference to Letter No / Date: a. 230/DSDT-KTTD, received 21/02/2023 b. UJV-MLT-00074-23-B-UJV, dated 07/02/2023 at ee oh Dear Sirs, UJV acknowledges receipt of MBR's letter ref [a] whereby MRB requested the JV of Verification Consultant to coordinate closely with relevant parties including CP06 Contractor during the implementation process of load test inspection. UJV regret to inform MRB that, unfortunately, UJV is currently unable to coordinate with JV of Verification Consultant since this activity is under suspension following UJV’s letter ref [b] However, please rest assured that UJV is doing its best to resolve this situation and will provide its full support once the suspension is lifted. UJV apologises for the inconvenience this may cause. Am Project Director Unincorporated Joint Venture On behalf of Unincorporated Joint Venture for: Alstom Transport SA, Colas Rail SAS, Thales SIX GTS France SAS, UJV-MLT-00098 .23-E-UJV dated: 21/02/2023 ALSTOM Transport S.A. ~ HANOI LINE 3/ CP06 Project Office , Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
Contract Package No 06: Delayed approval of CP06 RAMS documentation by the Engineer | tu {NS SERB JOINT VENTURE ALSTOM =m THALES Hanoi, 09/02/2021 To the attention of; Mr. Philippe BLANCHO - SYSTRA Project Director Systra Hanoi Metro Project Office 12" floor — Hoa Binh Building,106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son - Manager of Project Implementation (PID1 Management) Hanoi Metropolitan Raiway Management Board (MRB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hoang Mai, Hanoi Subject: Contract Package No 06: Delayed approval of CP06 RAMS documentation by the Engineer UJV Letter Reference No: UJV-MLT-00102-21-E-UJV Reference to Letter No/ Date: N/A 3 5 4 A + Dear Sirs, The purpose of this letter is to alert about the continuous issues to obtain the Non-Objection from the Engineer on CP06 RAMS documentation: Between September 2020 and December 2020, each week, PMG and all CP06 subgroups held RAMS workshops with the Engineer (Tadeusz CICHOCK! -PIC RAMS expert on Hanoi L3 project) with the purpose to validate CP06 RAMS design documentation. As a result of these workshops, we reached an agreement with a proposed SONO status given by the Engineer on eighteen (18) CP06 RAMS documents (refer to table 1 below and the attachment #1 enclosed to this letter). Despite the agreement in principle on these SONO status, with advanced review sheets sent by e-mail, CP06 has finallly received letters from the Engineer wherein all these documents came back one by one with REJECTED status (refer to table 1 and attachment #2 enclosed to this letter). Hereunder, the table gives a synthesis of CP06 RAMS documents reviewed with the Engineer and the status given during the workshops and the status given by the Engineer through letters: ¦ UJV-MLT-00102-21-E-UJV dated:09/02/2021 Page 1/3 ALSTOM Transport S.A. = HANOI LINE 3 / CP06 Project Office Sulte 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
Contract Package No 06: Delayed approval of CP06 RAMS documentation by the Engineer | tu {NS SERB JOINT VENTURE ALSTOM =m THALES Hanoi, 09/02/2021 To the attention of; Mr. Philippe BLANCHO - SYSTRA Project Director Systra Hanoi Metro Project Office 12" floor — Hoa Binh Building,106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son - Manager of Project Implementation (PID1 Management) Hanoi Metropolitan Raiway Management Board (MRB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hoang Mai, Hanoi Subject: Contract Package No 06: Delayed approval of CP06 RAMS documentation by the Engineer UJV Letter Reference No: UJV-MLT-00102-21-E-UJV Reference to Letter No/ Date: N/A 3 5 4 A + Dear Sirs, The purpose of this letter is to alert about the continuous issues to obtain the Non-Objection from the Engineer on CP06 RAMS documentation: Between September 2020 and December 2020, each week, PMG and all CP06 subgroups held RAMS workshops with the Engineer (Tadeusz CICHOCK! -PIC RAMS expert on Hanoi L3 project) with the purpose to validate CP06 RAMS design documentation. As a result of these workshops, we reached an agreement with a proposed SONO status given by the Engineer on eighteen (18) CP06 RAMS documents (refer to table 1 below and the attachment #1 enclosed to this letter). Despite the agreement in principle on these SONO status, with advanced review sheets sent by e-mail, CP06 has finallly received letters from the Engineer wherein all these documents came back one by one with REJECTED status (refer to table 1 and attachment #2 enclosed to this letter). Hereunder, the table gives a synthesis of CP06 RAMS documents reviewed with the Engineer and the status given during the workshops and the status given by the Engineer through letters: ¦ UJV-MLT-00102-21-E-UJV dated:09/02/2021 Page 1/3 ALSTOM Transport S.A. = HANOI LINE 3 / CP06 Project Office Sulte 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
Contract Package No 06: Contractor’s right to terminate the Contract | U(photoao UNINCORPORATED JOINT VENTURE ALSTOM. THALES Hanoi, 28/02/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU - SYSTRA Project Director Systra Hanoi Metro Project Office 412" floor - Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Contractor’s right to terminate the Contract UJV Letter Reference No: UJV-MLT-00107-23-E-UJV Reference to Letter No/ Date: a. UJV-MLT-00027-23-E-UJV, dated 14/01/2023 b. UJV-MLT-00074-23-E-UJV, dated 07/02/2023 Dear Sirs, We refer to our letter ref [a] notifying you of: 1. Your failure to pay the certified IPC 36 within the timeframe stipulated under Sub-Clause 14.7, i.e., by 14 January 2023 (being 56 days after the Engineer received the Contractor's Statement and supporting documents on 19 November 2022), and 2. Our right to suspend the Works unless and until we received the full amount certified in IPC 36. As no payment was subsequently made, we informed you by our letter ref [b] that we had partially suspended the Works in accordance with Sub-clause 16.1. It is now well beyond 14 January 2023, and we have still not received the amount due under IPC 36. We therefore wish you to inform you that, in those circumstances, we are entitled to issue a notice of termination pursuant to Sub-Clause 16.2 of the Contract and that we reserve all of our rights in this regard. Project Director Unincorporated Joint Venture On behalf of Unincorporated Joint Venture for: Alstom Transport SA, Colas Rail SAS, Thales SIX GTS France SAS, UJV-MLT-00107-23-E-UJV dated: 28/02/2023 ALSTOM Transport S.A. — HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
Contract Package No 06: CP6 requesting for report on the status train registration implementation | J) L Í ôn ERIE JOINT VENTURE ALSTOM <i> THALES Hanoi, 09/03/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy to: Mr. Alain BECHEREAU — SYSTRA Project Director Systra Hanoi Metro Project Office 12th floor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: CP6 requesting for report on the status train registration implementation UJV Letter Reference No: UJV-MLT-00114-23-E-UJV Reference to Letter No / Date: a. MRB letter 273 DSDT/THDA1, received 23/02/2023 Dear Sirs, Following MRB request in letter [a], UJV would like to response as followings: 1. All documentation requested by VR based on QCVN18:2018 have been provided by UJV to VR 2. All inspection requested by VR based on QCVN18:2018 have been performed by UJV with VR > ONE minor pending point: ¢ 3 DDU (Digital Display units) out of 20 need reinspection e Issue is with one button: “Navigate push button to switch language VN/EN & Maintenance tab access” e 2 DDU already have already been replaced by UJV e 30DUs are scheduled to be re-inspected by VR before end of March 2023 e VR is requesting the re-inspection as per QCVN18:2018 - Chapter 2.3.4.17 c: “An unloaded train (not carrying passengers) shall possibly tow another train carrying full load without the propulsion operating on the highest slope of the main line to the next station” , however: e This test was successfully performed in Hanoi on the 11/10/2021 following the approved test procedure reference # U.JV-IMP-PRC-RSK-L00-50229-E-4A. e Invitation was sent to VR,however unfortunately VR was unavailable for this Witness. UJV-MLT-00114-23-E-UJV 5 dated: 09/03/2023 Page 1/2 ALSTOM Transport S.A. - HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
Contract Package No 06: Selected supplier for Platform Mirror | ụ JŸh UNINCORPORATED JOINT VENTURE ALSTOM au THALES Hanoi, 06/03/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy to: Mr. Alain BECHEREAU - SYSTRA Project Director Systra Hanoi Metro Project Office 12% floor — Hoa Binh Building,106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Selected supplier for Platform Mirror UJV Letter Reference No: UJV-MLT-00115-23-E-UJV Reference to Letter No/ Date: a. UJV-MLT-00773-22-B-UJV, dated 18/11/2022 b. PIC-MLT-04292-22-EV, received 16/12/2022 c. 118/DSDT-THDA1, received 07/02/2023 d. PIC-MLT-00754-23-E, received 24/02/2023 Dear Sirs, UJV refers to MRB’s letter ref [c] whereby UJV was requested to provide the missing ISO certificate. UJV would like to inform you that, UJV has been working with its supplier to acquire the related [SO certificate. However, until the date of this letter, UJV is still unable to obtain this ISO from the supplier. Nevertheless, it is to highlight that platform mirror is only an alternative option, and it is out of scope of CP06 contract, UJV provided platform mirrors as a gesture of goodwill. Therefore, there is no contractual requirement for this equipment. Please refer to UJV-TEC-TTS-UJV-L00-01012-E-2A-D100-6.01 Hardware Requirement Specification — Platform Mirror (SONO on 01/12/2022) which is clearly state that: “There is no Contractual Requirement related to the Platform mirror, it is an alternative option in case of platform monitor loss, but not considered as an equivalent option. Platform mirror is an alternative option in case of platform monitor loss. but not an option to replace platform monitor.” UJV also wish to ciarify that since it is not under UJV's control, UJV has never committed to acquire the said ISO certificate from the supplier as stated by the Engineer in its letter ref (dj. ¦ UJV trusts the above clarified its position. Ï Yours faithfully, ¦ [ UJV-MLT-00115-23-E-UJV ˆ dated: 06/03/2023 ¦ page 1/2 ALSTOM Transport S.A. ~ HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0124 3956 4999 - Fax: +84 (0)24 3967 4999
Contract Package No 06: CP06 Progress Minutes of Meeting on 24 February 2023 A | UV UNINCORPORATED JOINT VENTURE ALSTOM myn THALES Hanoi, 06/03/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son - Vice General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Alain BECHEREAU — SYSTRA Project Director Systra Hanoi Metro Project Office 12" fioor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: CP06 Progress Minutes of Meeting on 24 February 2023 A UJV Letter Reference No: UJV-MLT- 00116-23-E-UJV by fr a\" Reference to Letter No / Date: a. UJV-MLT-00093-23-E-UJV, dated 20/02/2023 4À Dear Sirs, Upor the call from the Contractor to conduct a meeting with the Employer and the Engineer to solve pending points in term of CP06 progress (letter ref [a]), all parties managed to attend the meeting on 24 February 2023 at the Employer's Office. UJV is pleased to attach with this letter the Minute of Meeting for signature of the Employer and the Engineer. Thank you for your coordination. ĐỖ THỊ THÍ ĐI THÀNH PHO) Hà QC Project Director Unincorporated Joint Venture ; On behalf of Unincorporated Joint Venture for: Alstom Transport SA, Colas Rail SAS, Thales SIX GTS France SAS, Copy to: - UJ Sub-Groups Project Managers Attachment: - PIC-MOM-00883-23-B [ VIV-MLT- 00116-23-E-UJV 7 dated: 06/03/2023 , Page: 1/1 ‘¦ ALSTOM Transport S.A. - HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 — Fax: +84 (0)24 3967 4999
Contract Package No 06: Impact of Covid-19 - Submission of IC#12 | Ổ) \; Á lôi tanuer JOINT VENTURE ALSTOM wile THALES To the attention of: Copy to: Subject: UJV Letter Reference No: Reference to Letter No Dear Sirs, ate: Hanoi, 25/02/2021 ' Mr. Philippe BLANCHO - SYSTRA Project Director Systra Hanoi Metro Project Office 12% floor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mal, Hanoi Mr. Nguyen Ba Son - Manager of Project impfementation (PID1 Management) Hanoi Metropolitan Railway Management Board (MRB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hoang Mai, Hanoi Contract Package No 06: Impact of Covid-19 - Submission of IC#12 UJV-MLT-00128-21-E-UJV a. PIC-MLT-00757-21-E received 22/02/2021 b. UJV-MLT-00060-21-E dated 25/01/2021 c. PIC-MLT-07467-20-E received 24/12/2020 Ị d. UJV-MLT-01230-20-E dated 17/12/2020 - ø. PIC-MLT-07049-20-E received 04/12/2020 {. UJV-MLT-01133-20-E dated 25/11/2020 g. PIC-MLT-06515-20-E recelved 08/11/2020 h. UJV-MLT-01059-20-E dated 28/10/2020 i. PIC-MLT-05760-20-£ recelved 02/20/2020 J. UJV-MLT-00981-20-E dated 28/09/2020 k. PIC-MLT-05070-20-E received 26/08/2020 ¦. UJV-MLT-00867-20-E dated 21/08/2020 m. PIC-ML.T-04578-20-E received 03/08/2020 m. UJV-MLT-00781-20-E dated 21/07/2020 o. PIC-MLT-03854-20-E received 06/07/2020 p. UJV-MLT-00669-20-E dated 18/06/2020 q. PIC-MLT-03030-20-E received 26/05/2020 r. UJV-MLT-00638-20-E dated 18/05/2020 s. PIC-MLT-01610-20-E received 14/04/2020 Please find attached the Interim Claim #12 linked to the impact of Covid-19, with cut-off date 25 January 2021. As the event is continuing we will continue to provide updates of the Claim on a monthly basis in accordance with Clause 20.1 of the Conditions of Contract. Please rest assured that UJV is doing its best efforts to mitigate the continuing impacts of the Covid-19 on the Project. UdV-MLT-00128-21-E-UJV ~ dated: 25/02/2021 ® Page 1/2 ALSTOM Transport S.A. - HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: ed (0)24 3956 4999 ~ Fax: +84 (0)24 3967 4999
Contractor’s right to terminate the Contract due to the failure of the Employer to comply with Sub-Clause 2.4 | Ễ iy Í Tối GENCUKE JOINT VENTURE ALSTOM -%Ð&- THALES Hanoi, 20/03/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son — Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU — SYSTRA Project Director Systra Hanoi Metro Project Office 121 floor - Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Contractor’s right to terminate the Contract due to the failure of the Employer to comply with Sub-Clause 2.4 UJV Letter Reference No: UJV-MLT-00152-23-E-UJV Reference to Letter No/ Date: a. UJV-MLT-00065-23-B-UJV, dated 03/02/2023 b. 333/DSDT-DA1, received 03/03/2023 c. UJV-MLT-00107-23-E-UJV, dated 28/02/2023 Dear Sirs, UJV acknowledges receipt of the Employer's letter ref [b] whereby the Employer objected the notice of suspension of work as well as the UJV's right to terminate the Contract. UJV would like to respond as follows: 1. 2. Regarding of delayed payment IPC no.36: UJV has submitted its letter ref [c] to confirm its entitlement to suspend or terminate the Contract. Regarding of the Employer's financial arrangement: The Employer does not understand its responsibility as well as its obligation under the Contract, in regard to demonstration of financial arrangements by providing reasonable evidence in compliance with Sub-Clause 2.4 [Employer's Financial Arrangement] of the General Conditions of Contract. Indeed, the reply from the Employer through its letter ref [b], stating that HPC has approved for the arrangement of additional budget for the project from the HPC’s State budget and the medium- term investment budget plan, is simply not enough nor the mere communication of the existence of funds in the accounts of the Employer. The evidence should be reasonable, the information provided by the Employer in its letter ref [b] does not constitute reasonable evidence that financial arrangements for payment of any additional variation or EoT have been made or are being maintained. For completeness, UJV regrets to remind the Employer that, in accordance with Sub-Clause 16.2 [Termination by Contractor] of the General Conditions of Contract, UJV is now entitled to issue a notice of termination in respect of the Employer's failure to comply with Sub-Clause 2.4 [Employer's Financial Arrangements] since UJV did not receive the reasonable evidence within 42 days after giving its notice in ref [a]. UJV reserves all rights under the Contract and/or at law in this regard. UJV-MLT-00152-23-E-UJV dated: 20/03/2023 AIL ALSTOM Transport S.A. - HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
Notice of event under Clause 8.4 and 20.1 - Delayed communication of ISA reports | WU) {RN ENC URE JOINT VENTURE ALSTOM .@@- THALES Hanoi, 12/03/2021 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son - Manager of Project Implementation (PID1 Management) Hanoi Metropolitan Railway Management Board (MRB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hoang Mai, Hanoi Mr. Philippe BLANCHO - SYSTRA Project Director Systra Hanoi Metro Project Office 12" floor - Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: Notice of event under Clause 8.4 and 20.1 - Delayed communication of ISA reports UJV Letter Reference No: UJV-MLT-00179-21-E-UJV Reference to Letter No / Date: a. 217/DSDT-DA1 received 26/02/21 b. UJV-MLT-00186-21 dated 04/03/21 c. UJV-MLT-00123-21 dated 24/02/24 d. UJV-MLT-00107-21 dated 19/02/21 @. 166/DSDT-DA1 received 09/02/21 Dear Sirs, We acknowledged receipt of MRB letter above captioned {a] on 26 February 2021 enclosing the updated report No2 - (version 2 dated 12/10/2020) and the report No 3 (version No 1 dated 26/11/2020) from the ISA (ABC JV). As indicated in our letter [d), UJV was not aware of these reports related to Verification and Certification of System Safety, until the Safety Notice No2 of ISA for energization and dynamic tests was received on 9 February 2021, through MRB letter ref [e]. The first train run was performed on 22 January 2021, following the approval of the related Test Readiness Review (TRR) by the Engineer, while MRB had not informed that the start of dynamic tests could potentially be conditional upon the authorization of the ISA contracted by MRB. In addition, there is no such requirement for ISA approval prior to dynamic tests in CP06 Contract. This lack of communication from MRB regarding ISA safety reports and associated concerns has generated an unclear situation with conflicting information communicated to UJV. On the one hand, as already mentioned in previous correspondences referenced above, UJV received the approval of the Engineer to start dynamic tests on 22 January 2021 based on the outcome of the review of UJV Safety report for tests during the Test Readiness Review ref. CP06-TRR-0015. On the other hand, MRB informed UJV on 9 February 2021 about ISA safety notice and recommendations for the start of [ UJV-MLT-00179-21-E-UJV : dated: 12/03/2021 page 12 ALSTOM Transport S.A. - HANOI! LINE 3/ CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: hà (0)24 3956 4999 — Fax: +84 (0)24 3967 4999
UJV response to MRB comments on payment procedure for IPC 36 and IPC37 | DJV UNINCORPORATED JOINT VENTURE ALSTOM -4$È&- THALES Hanol, 13/04/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son - Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU — SYSTRA Project Director Systra Hanoi Metro Project Office 42% floor - Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: UJV response to MRB comments on payment procedure for IPC 36 and IPC37 UJV Letter Reference No: UJV-MLT-00189-23-E-UJV Reference to Letter No / Date: a. 579/DSDT-THDA1, received 12/04/2023 Dear Sirs, UJV acknowledges receipt of MRB's letter ref [a] whereby MRB provided its excuses not to pay for the amount rel to the Variation of Temporary LV panels certified in IPC 36 as well as the amount related to the Variation of Additi Training certified in IPC 37. UJV is very surprised with this statement from MRB and totally disagrees with MRB's position. Dealing with the approval from competent authorities for the increase in cost estimate of any Variation related to CP06 package is none of UJV's business and is purely the internal work of MRB. This process should have been done before any confirmation from MRB to allow the Engineer to issue its Instruction to UJV. Because of this wrong internal MRB procedure, MRB has substantially failed to perform its obligation under the Contract to pay UJV the amount due under above-mentioned IPC. It has materially and adversely affected the economic balance of UJV and the ability of UJV to perform the contract. UJV, once again, requests MRB to pay UJV, without further delay, the full amount of certified IPC as per provisions of Contract. UJV reserves its right under the Contract and/or at law. UJV-MLT-00189-23-E-UJV dated: 13/04/2023 Pago: 1/2 ALSTOM Transport S.A. - HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
UJV response to MRB comments on payment procedure for IPC 36 and IPC37 | DJV UNINCORPORATED JOINT VENTURE ALSTOM -4$È&- THALES Hanol, 13/04/2023 To the attention of: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi. Mr. Nguyen Ba Son - Vice General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Copy Mr. Alain BECHEREAU — SYSTRA Project Director Systra Hanoi Metro Project Office 42% floor - Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Subject: Contract Package No 06: UJV response to MRB comments on payment procedure for IPC 36 and IPC37 UJV Letter Reference No: UJV-MLT-00189-23-E-UJV Reference to Letter No / Date: a. 579/DSDT-THDA1, received 12/04/2023 Dear Sirs, UJV acknowledges receipt of MRB's letter ref [a] whereby MRB provided its excuses not to pay for the amount rel to the Variation of Temporary LV panels certified in IPC 36 as well as the amount related to the Variation of Additi Training certified in IPC 37. UJV is very surprised with this statement from MRB and totally disagrees with MRB's position. Dealing with the approval from competent authorities for the increase in cost estimate of any Variation related to CP06 package is none of UJV's business and is purely the internal work of MRB. This process should have been done before any confirmation from MRB to allow the Engineer to issue its Instruction to UJV. Because of this wrong internal MRB procedure, MRB has substantially failed to perform its obligation under the Contract to pay UJV the amount due under above-mentioned IPC. It has materially and adversely affected the economic balance of UJV and the ability of UJV to perform the contract. UJV, once again, requests MRB to pay UJV, without further delay, the full amount of certified IPC as per provisions of Contract. UJV reserves its right under the Contract and/or at law. UJV-MLT-00189-23-E-UJV dated: 13/04/2023 Pago: 1/2 ALSTOM Transport S.A. - HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999
Notice of delayed mobilisation of O&M staff for Rolling Stock training | WW) {RE CURE JOINT VENTURE ALSTOM -##. THALES Hanoi, 03/12/2020 To the attention of: Mr. Philippe BLANCHO - SYSTRA Project Director Systra Hanoi Metro Project Office 12" floor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Copy to: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son - Manager of Project Implementation (PID1 Management) Hanoi Metropolitan Raiway Management Board (MRB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hoang Mai, Hanoi Subject: Contract Package No 06: Notice of delayed mobilisation of O&M staff for Rolling Stock training UJV Letter Reference No: UJV-MLT-01159-20-E-RSK Reference to Letter No/ Date: a.89/TB-DSDT received 02/06/2020 b. PIC-MLT-03338-20-E received 10/06/2020 c. UJV-MLT-00650-20-RSK dated 16/06/2020 Dear Sirs, We refer to UJV's letter above captioned [c] whereby we requested MRB to confirm the availability of Hanoi Metro Company ("HMC") trainees to attend the driver's training which was planned to start on 19 of November 2020 in Valenciennes (France). To date we have not received any response to our letter. We also refer to MRB’s letter above captioned [a] informing that HMC will not provide staff to attend training sessions before November 2020 at the earliest, and requesting the Contractors to adapt the training schedule accordingly. Following the meeting held on 22 October 2020 we received Engineer’ s letter [b] providing an updated Training Schedule to the Contractors. According to the Approved Baseline Programme, Rolling Stock trainings were due to start on the 9th of December 2020. Delayed mobilisation of O&M staff to attend the trainings may affect our ability to comply with our obligations and delay the progress of the Works. UJV hereby gives notice under Sub-Clause 8.4 [Extension of time] and 20.1 [Contractor's claim] of the Conditions of Contract for all delay and potential costs associated with delayed mobilization of O&M staff for Rolling Stock trainings. UJV propose to submit a claim file when this delay starts affecting the progress of the Works. All delay events associated with delayed mobilization of the O&M Entity, including Delayed input from MRB (Maintenance team ready for training) to CP06 UJV-MLT-01159-20-E-RSK dated: 03/12/2020 Pape 2 ¦ ALSTOM Transport S.A. - HANOI LINE 3 / CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 - Fax: +84 (0)24 3967 4999 4
Notice of Claim under Clause 8.4 and 20.1 for delayed completion of earthing connection of false floor by CP02 | J) À {a reece JOINT VENTURE ALSTOM === THALES Hanoi, 22/12/2020 To the attention of: Mr. Philippe BLANCHO - SYSTRA Project Director Systra Hanoi Metro Project Office 12 floor — Hoa Binh Building, 106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Copy to: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Raiway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son - Manager of Project implementation (PID1 Management) Hanoi Metropolitan Railway Management Board (MRB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hoang Mai, Hanoi Subject: Contract Package No 06: Notice of Claim under Clause 8.4 and 20.1 for delayed completion of earthing connection of false floor by CP02 UJV Letter Reference No: UJV-MLT-01249-20-E-APW Reference to Letter No / Date: a. PIC-MLT-05997-20-B received 14/10/2020 Dear Sirs, UJV refers to PIC letter ref. [a], regarding energization plan of third rail. UJV would like to highlight that the schedule of Power On is as follows: Power On as per Approved Baseline Programme 4A h Station 01 31-Dec-19 =I Station 02 31-Dec-19 3 Station 03 14-Jan-20 4 Station 04 4-Feb-20 a Station 05 28-Feb-20 6 Station 06 13-Mar-20 7 Station 07 4-May-20 =¦ Station 08 28-May-20 9 Station 09 1-Sep-20 10 Station 10 17-Sep-20 11 ¦ Station 11 19-Oct-20 12 Station 12 ~ 17-Nov-20 UJV-MLT-01249-20-E-APW — - dated: 22/42/2020 ˆ page aa ALSTOM Transport S.A. - HANOI LINE 3/ CP06 Project Office Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 (0)24 3956 4999 — Fax: +84 (0)24 3967 4999
Contract Package No 06: Impact of Covid-19 - Submission of iC#7 | Í U NY ea JOINT VENTURE ALSTOM =tw THALES Hanol, 28/09/2020 To the attention of: Mr. Philippe BLANCHO - SYSTRA Project Director Systra Hanoi Metro Project Office ' 12 floor — Hoa Binh Building,106 Hoang Quoc Viet Street, Cau Giay District, Hanoi Copy to: Mr. Nguyen Cao Minh - General Director Hanoi Metropolitan Railway Management Board (MRB) CC2 Building, Dong Tau Urban Area, Thinh Liet, Hoang Mai, Hanoi Mr. Nguyen Ba Son - Manager of Project Implementation (PID1 Management) Hanoi Metropolitan Railway Management Board (MRB) PID1 Room, 3rd Floor, CC2 Building, Dong Tau Urban Area, Hoang Mai, Hanoi Subject: Contract Package No 06: Impact of Covid-19 - Submission of iC#7 UJV Letter Reference No: U.JV-MLT-00981-20-E-UJV Reference to Letter No / Date: a. PIC-MLT-05070-20-E recelved 26/08/2020 h b. UJV-MLT-00867-20-E dated 21/08/2020 c. PIC-MLT-04578-20-E received 03/08/2020 d. UJV-MLT-00781-20-E dated 21/07/2020 : e. PIC-MLT-03854-20-E received 06/07/2020 f. UJV-MLT-00669-20-E dated 18/06/2020 g. PIC-MLT-03030-20-E received 26/05/2020 h. UJV-MLT-00538-20-E dated 18/05/2020 ¦. PIC-MLT-01610-20-E received 14/04/2020 ALST, fo _ ——<w Dear Sirs, Reference is made to the Engineer's letter [a]. We have already expressed our detailed position on all the points mentioned in your letter through previous correspondence referenced above. As the event is continuing, we hereby provide in Attachment #1 the Interim Claim #7, with cut-off date 25 August 2020 and will continue to provide updates of the Claim on a monthly basis in accordance with Clause 20.1 of the Conditions of Contract. Doan Viet Dung ef of Project Office Unincorporated Joint Venture Alstom Transport SA, Colas Rail S.A., Thales Communications & Security S.A.S. ¦ UJV-MLT-00981-20-E-UJV dated: 28/09/2020 Pago 1/2 ALSTOM Transport S.A. ~ HANOI LINE 3/ CP06 Project Office , 77 Suite 902, Capital Tower, 109 Tran Hung Dao Street, Cua Nam Ward, Hoan Kiem District, Hanoi, Vietnam Tel: + 84 ow 3956 4999 — Fax: +84 (0)24 3967 4999